## Sheet1
No. | Task | LongDB | LuLP | TungNT | DucNT | Unit | Size | Deadline | Deliverables | DONE
1 | Project Information |  |  |  | O
| Scenario problems |  |  | O
| Solutions | O
| Approaches |  | O | [6 empty] | O
Others
….
2 | Problem Definition
Project organization
Project management plan
Coding Convention
…..
1 | Screen design
2 | Customers interfaces |  |  | O | [5 empty] | O
3 | Staffs interfaces |  |  |  | O
4 | Administrators interfaces |  | O
5 | Database design
6 | ERD | O | O | O | O |  |  |  | ERD | O
7 | Logical DB
8 | Physical DB |  | O | [6 empty] | O
9 | SRS | [6 empty] | 2014-02-15
10 | Usecase
11 | Guest |  |  |  |  | 2 |  | 2014-02-15
12 | Register | [6 empty] | 2014-02-15 | Use-case specification
13 | Search | O | [5 empty] | 2014-02-15 | Use-case specification
14 | Customer |  |  |  |  | 10 |  | 2014-02-15
15 | Post request | [6 empty] | 2014-02-15 | Use-case specification
16 | Edit request | [6 empty] | 2014-02-15 | Use-case specification
17 | Cancel request | [6 empty] | 2014-02-15 | Use-case specification
18 | Payment | [6 empty] | 2014-02-15 | Use-case specification
19 | Search request | [6 empty] | 2014-02-15 | Use-case specification
20 | Tracking | O | [5 empty] | 2014-02-15 | Use-case specification
21 | View request detail | [6 empty] | 2014-02-15 | Use-case specification
22 | Statistics | [6 empty] | 2014-02-15 | Use-case specification
23 | Comment | [6 empty] | 2014-02-15 | Use-case specification
24 | Rating | [6 empty] | 2014-02-15 | Use-case specification
25 | Administrators |  |  |  |  | 7 |  | 2014-02-15
26 | Define fee value/formular | [6 empty] | 2014-02-15 | Use-case specification
27 | Edit fee value/formular | O | [5 empty] | 2014-02-15 | Use-case specification
28 | Create new staff account | [6 empty] | 2014-02-15 | Use-case specification
29 | Edit account info | [6 empty] | 2014-02-15 | Use-case specification
30 | Delete account | [6 empty] | 2014-02-15 | Use-case specification
31 | Search information | [6 empty] | 2014-02-15 | Use-case specification
32 | Statistics | [6 empty] | 2014-02-15 | Use-case specification
33 | Staffs |  |  |  |  | 21 |  | 2014-02-15
34 | Approve request | O |  | O |  |  |  | 2014-02-15 | Use-case specification
35 | Reject request |  |  | O |  |  |  | 2014-02-15 | Use-case specification
36 | Assisgn package |  |  | O |  |  |  | 2014-02-15 | Use-case specification
37 | Update package status |  |  | O |  |  |  | 2014-02-15 | Use-case specification
39 | Manage time |  |  | O |  |  |  | 2014-02-15 | Use-case specification
40 | Search package info |  |  | O |  |  |  | 2014-02-15 | Use-case specification
41 | Statistics |  |  | O |  |  |  | 2014-02-15 | Use-case specification
43 | Add trip | O | [5 empty] | 2014-02-15 | Use-case specification | O
44 | Edit trip | [6 empty] | 2014-02-15 | Use-case specification | O
45 | Delete trip | [6 empty] | 2014-02-15 | Use-case specification | O
47 | Add station | [6 empty] | 2014-02-15 | Use-case specification | O
48 | Edit station | [6 empty] | 2014-02-15 | Use-case specification | O
49 | Delete station | [6 empty] | 2014-02-15 | Use-case specification | O
51 | Add route | [6 empty] | 2014-02-15 | Use-case specification | O
52 | Edit route | O | [5 empty] | 2014-02-15 | Use-case specification | O
53 | Delete route | [6 empty] | 2014-02-15 | Use-case specification | O
54 | Add coach | [6 empty] | 2014-02-15 | Use-case specification | O
55 | Edit coach | [6 empty] | 2014-02-15 | Use-case specification | O
56 | Delete coach | [6 empty] | 2014-02-15 | Use-case specification | O
57 | Delete comment | [6 empty] | 2014-02-15 | Use-case specification
58 | Clear rating | [6 empty] | 2014-02-15 | Use-case specification
59 | Coding
60 | Coaches, coache types, volume management |  |  |  | O
61 | Scheduling, assigning, staffs management |  | O
62 | Trips, routes, stations management | O
63 | Requests, packages, comments and rating management |  |  | O
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
Note on B2: phuong: Each row is a topic in project document. Do not have more than 15 rows in each product deliverable. Content in this template is used for reference only and it is vary in each project
Note on C2: phuong: Only one member in line, who has main repsonsibilty in this task