## Sheet1
No. | Task | LongDB | LuLP | TungNT | DucNT | Deadline | MISSED | Notes
1 | Project Information |  |  |  | O
| Scenario problems |  |  | O
| Solutions | O
| Approaches |  | O |  |  |  | O
Others
….
2 | Problem Definition
Project organization
Project management plan
Coding Convention
…..
1 | Screen design
2 | Customers interfaces |  |  | O
3 | Staffs interfaces |  |  |  | O |  | O | Chưa có giao diện của Staff
4 | Administrators interfaces |  | O |  |  |  | O | Chưa có giao diện của Admin
5 | Database design
6 | ERD | O | O | O | O
7 | Logical DB
8 | Physical DB |  | O |  |  |  | O | Chưa update lại DB theo yêu cầu của thầy ngày 24/01/2014
9 | SRS |  |  |  |  | 2014-02-15
10 | Usecase
11 | Guest |  |  |  |  | 2014-02-15
12 | Register |  |  |  | O | 2014-02-15
13 | Search |  |  |  | O | 2014-02-15
14 | Customer |  |  |  |  | 2014-02-15
15 | Post request |  |  |  | O | 2014-02-15
16 | Edit request |  |  |  | O | 2014-02-15
17 | Cancel request |  |  |  | O | 2014-02-15
18 | Payment |  |  |  | O | 2014-02-15
19 | Search request |  |  |  | O | 2014-02-15
20 | Tracking |  |  |  | O | 2014-02-15
21 | View request detail |  |  |  | O | 2014-02-15
22 | Statistics |  |  |  | O | 2014-02-15
23 | Comment |  | O |  |  | 2014-02-15
24 | Rating |  | O |  |  | 2014-02-15
25 | Administrators |  |  |  |  | 2014-02-15
26 | Define fee value/formular |  | O |  |  | 2014-02-15
27 | Edit fee value/formular |  | O |  |  | 2014-02-15
28 | Create new staff account |  | O |  |  | 2014-02-15
29 | Edit account info |  | O |  |  | 2014-02-15
30 | Delete account |  | O |  |  | 2014-02-15
31 | Search information |  | O |  |  | 2014-02-15
32 | Statistics |  | O |  |  | 2014-02-15
33 | Staffs |  |  |  |  | 2014-02-15
34 | Approve request |  |  | O |  | 2014-02-15
35 | Reject request |  |  | O |  | 2014-02-15
36 | Assisgn package |  |  | O |  | 2014-02-15
37 | Update package status |  |  | O |  | 2014-02-15
39 | Manage time |  |  | O |  | 2014-02-15
40 | Search package info |  |  | O |  | 2014-02-15
41 | Statistics |  |  | O |  | 2014-02-15
43 | Add trip | O |  |  |  | 2014-02-15
44 | Edit trip | O |  |  |  | 2014-02-15
45 | Delete trip | O |  |  |  | 2014-02-15
47 | Add station | O |  |  |  | 2014-02-15
48 | Edit station | O |  |  |  | 2014-02-15
49 | Delete station | O |  |  |  | 2014-02-15
51 | Add route | O |  |  |  | 2014-02-15
52 | Edit route | O |  |  |  | 2014-02-15
53 | Delete route | O |  |  |  | 2014-02-15
54 | Add coach | O |  |  |  | 2014-02-15
55 | Edit coach | O |  |  |  | 2014-02-15
56 | Delete coach | O |  |  |  | 2014-02-15
57 | Delete comment |  | O |  |  | 2014-02-15
58 | Clear rating |  | O |  |  | 2014-02-15
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
Note on B2: phuong: Each row is a topic in project document. Do not have more than 15 rows in each product deliverable. Content in this template is used for reference only and it is vary in each project
Note on C2: phuong: Only one member in line, who has main repsonsibilty in this task