## Sheet1
No. | Product Deliverables | Task | LongDB | LuLP | TungNT | DucNT | Unit | Size | Deadline | Deliverables | DONE
1 | Report1 - Introduction | Project Information |  |  |  | O
|  | Scenario problems |  |  | O
|  | Solutions | O
|  | Approaches |  | O | [6 empty] | O
Others
….
2 | Report2- Software Project Management Plan | Problem Definition
Project organization
Project management plan
Coding Convention
…..
3 | Report 3- Software Requirement Specification | User Requirement Specification
|  | Guest Requirements |  |  |  | O |  |  |  | Outline document
|  | Customers Requirements |  |  | O |  |  |  |  | Outline document
|  | Staffs Requirements |  | O | [5 empty] | Outline document
|  | Administrators Requirements | O | [6 empty] | Outline document
System Requirement Specification
|  | External Interface Requirements | O
|  | Main Flow overview | O | [6 empty] | Main Flow overview
Functional Requirement
|  | Usecase | [6 empty] | 2014-02-10 | Use-case specification
|  | Guest |  |  |  |  | 2 |  | 2014-02-10
|  | Register |  |  |  | O |  |  | 2014-02-10 | Use-case specification
|  | Search |  |  |  | O |  |  | 2014-02-10 | Use-case specification
|  | Customer |  |  |  |  | 10 |  | 2014-02-10
|  | Post request |  |  |  | O |  |  | 2014-02-10 | Use-case specification
|  | Edit request |  |  |  | O |  |  | 2014-02-10 | Use-case specification
|  | Cancel request |  |  |  | O |  |  | 2014-02-10 | Use-case specification
|  | Payment |  |  |  | O |  |  | 2014-02-10 | Use-case specification
|  | Search request |  |  |  | O |  |  | 2014-02-10 | Use-case specification
|  | Tracking |  |  |  | O |  |  | 2014-02-10 | Use-case specification
|  | View request detail |  |  |  | O |  |  | 2014-02-10 | Use-case specification
|  | Statistics |  |  |  | O |  |  | 2014-02-10 | Use-case specification
|  | Comment |  | O |  |  |  |  | 2014-02-10 | Use-case specification
|  | Rating |  | O |  |  |  |  | 2014-02-10 | Use-case specification
|  | Administrators |  |  |  |  | 7 |  | 2014-02-10
|  | Define fee value/formular |  | O |  |  |  |  | 2014-02-10 | Use-case specification
|  | Edit fee value/formular |  | O |  |  |  |  | 2014-02-10 | Use-case specification
|  | Create new staff account |  | O |  |  |  |  | 2014-02-10 | Use-case specification
|  | Edit account info |  | O |  |  |  |  | 2014-02-10 | Use-case specification
|  | Delete account |  | O |  |  |  |  | 2014-02-10 | Use-case specification
|  | Search information |  | O |  |  |  |  | 2014-02-10 | Use-case specification
|  | Statistics |  | O |  |  |  |  | 2014-02-10 | Use-case specification
|  | Staffs |  |  |  |  | 21 |  | 2014-02-10
|  | Approve request |  |  | O |  |  |  | 2014-02-10 | Use-case specification
|  | Reject request |  |  | O |  |  |  | 2014-02-10 | Use-case specification
|  | Assisgn package |  |  | O |  |  |  | 2014-02-10 | Use-case specification
|  | Update package status |  |  | O |  |  |  | 2014-02-10 | Use-case specification
|  | Manage time |  |  | O |  |  |  | 2014-02-10 | Use-case specification
|  | Search package info |  |  | O |  |  |  | 2014-02-10 | Use-case specification
|  | Statistics |  |  | O |  |  |  | 2014-02-10 | Use-case specification
|  | Add trip | O | [5 empty] | 2014-02-10 | Use-case specification
|  | Edit trip | O | [5 empty] | 2014-02-10 | Use-case specification
|  | Delete trip | O | [5 empty] | 2014-02-10 | Use-case specification
|  | Add station | O | [5 empty] | 2014-02-10 | Use-case specification
|  | Edit station | O | [5 empty] | 2014-02-10 | Use-case specification
|  | Delete station | O | [5 empty] | 2014-02-10 | Use-case specification
|  | Add route | O | [5 empty] | 2014-02-10 | Use-case specification
|  | Edit route | O | [5 empty] | 2014-02-10 | Use-case specification
|  | Delete route | O | [5 empty] | 2014-02-10 | Use-case specification
|  | Add coach | O | [5 empty] | 2014-02-10 | Use-case specification
|  | Edit coach | O | [5 empty] | 2014-02-10 | Use-case specification
|  | Delete coach | O | [5 empty] | 2014-02-10 | Use-case specification
|  | Delete comment |  | O |  |  |  |  | 2014-02-10 | Use-case specification
|  | Clear rating |  | O |  |  |  |  | 2014-02-10 | Use-case specification
Non-functional Requirement
Reliability
Availability
4 | Report 4- Software Design Description | 4.3 Component Diagram |  |  |  | O |  |  |  |  | O
4.4 Detailed Design
|  | 4.4.1 Entity Classes |  |  |  | O |  |  | 2014-02-21
|  | 4.4.2 Repository Classes | O | [5 empty] | 2014-02-21 |  | O
|  | 4.4.3 Algorithms Process Classes |  | O |  |  |  |  | 2014-02-22
|  | 4.4.4 Business Logic Classes |  |  | O |  |  |  | 2014-02-21
4.5. Behavioral Diagrams
|  | 4.5.1 State Machine Diagram 1 | O | [7 empty] | O
|  | 4.5.2 State Machine Diagram 2 | O | [7 empty] | O
4.5.3-n Sequence Diagram
|  | Sequence 1: Search Routes |  |  | O |  |  |  | 2014-02-26
|  | Sequence 2: Post Delivery Requests |  |  | O |  |  |  | 2014-02-26
|  | Sequence 3: Create a Trip | O | [5 empty] | 2014-02-26
|  | Sequence 4: Edit a Station | O | [5 empty] | 2014-02-26
|  | Sequence 5: Add a Price |  |  |  | O |  |  | 2014-02-26
|  | Sequence 8: Create a Staff Account |  |  |  | O |  |  | 2014-02-26
|  | Sequence 7: Approve Requests |  |  |  | O |  |  | 2014-02-26
|  | Sequence 8: Assign Package |  |  |  | O |  |  | 2014-02-26
4.6. User Interface Design
Home page
Page n
4.7. Database Design
|  | 4.7.1. Logical database design |  | O |  |  |  |  | 2014-02-20 |  | O
|  | 4.7.2. Physical database design |  | O |  |  |  |  | 2014-02-20 |  | O
5 | Report 5 - Software Implementation and Test Document | Setup Environtment
Module 1
Sub-Module 1.1
Sub-Module 1.2
Module 2
Sub-Module 1.1
Sub-Module 1.2
DB diagrams
Write Test case
Function 1
Function 2
Functuon n
Perform Testing
Function 1
Function 2
Others Testing
Function 1
Function 2
6 | Report 6 - Software User's Manual | Installation Guide
User’s Guide
Function 1
Function 2
Functuon n
Other
Notes
No. | Function Types | Function Point Size
1 | Insert, Delete, Update, Simple Search, Login, Register, simple function or simple query on one table | 1
2 | Computed functions or joined query | 2
3 | Complex functions or multiple subquery | 3
4 | Constraint process and data integrity | 4
5 | Functions with implementing algorithms | 5
Note on C2: phuong: Each row is a topic in project document. Do not have more than 15 rows in each product deliverable. Content in this template is used for reference only and it is vary in each project
Note on D2: phuong: Only one member in line, who has main repsonsibilty in this task
Note on C18: phuong: Use bold format for tasks which have sub-tasks
Note on C19: phuong: Use Indent for sub-tasks